## Slide 1: Product team operating model
T+IL Playbook
See file name for date and time of last update (e.g., 20190601 Product team operating model – T+IL playbook – v1230)

## Slide 2: Playbook context – product team operating model
Chapter
Description
File name
T+IL in a nutshell
An overview of the Lab’s scope, guiding principles, and purpose
[Date] T+IL nutshell - T+IL playbook - v[Time]
Lab operations
A high-level view of the Lab’s structure, governance, and operating model
[Date] Lab operations - T+IL playbook - v[Time]
Product team operating model
Overview of how product teams operate, including structure and ceremonies
[Date] Product team operating model - T+IL playbook – v[Time]
T+IL talent guide
An overview of all things talent for the Lab, including recruiting, capability-building, and performance management
[Date] T+IL talent guide - T+IL playbook - v[Time]
Onboarding playbook
A guide for people joining the Lab
[Date] Onboarding playbook - T+IL playbook - v[Time]
Product Lifecycle guide
Walkthrough of the Lab’s Product Lifecycle (PLC) governance, with detailed guidance for each review
[Date] PLC guidebook - T+IL playbook – v[Time]
This chapter

## Slide 3: Product teams’ agile operations are paramount to the success of the Lab
The Technology + Innovation Lab will operate under Agile methodologies focused on product deployments, sprints, and user stories
Agile development teams will be centered around the roles of product owner, scum master, and the development team
Product teams will consist of co-located business-facing product owners, multidisciplinary development teams, and agile resources (e.g., scrum masters, agile coaches)
Product development teams will work in rapid sprints following key agile ceremonies for governance and productivity

## Slide 4: The Lab will follow Agile methodologies focused on product deployments, sprints, and user stories
How
Where
Who
From today’s processes…
… to new Agile methodologies
Current project-oriented talent mix
New-age user and product-oriented talent mix
  Distinct positions grouped under separate functional/organizational units
  Consistent execution of agile methodologies: Product owners, scrum masters, and delivery teams
  Project-oriented teams is a mix of dedicated individuals and individuals supporting the project on a part-time basis
  Multi-functional, agile, product-based
Agile principles, with waterfall deployment cycles
Agile, iterative, and collaborative methodologies
  Silo’ed and specialized groups functionally aligned rather than product or user aligned
  Cross-functional groups collaborating across org. boundaries to deliver integrated solutions
  Plan-analyze-design-develop-test-deploy
  Continuous improvement through user story oriented sprints
  Agile methods but linear project-based work
  Iterative, 10-12-week product-based deployment cycles
Distributed, decentralized workforce
Unified and streamlined delivery teams
  Large distributed teams across multiple locations relying primarily on asynchronous communications
  Smaller, focuses co-located squads to target faster delivery and collaboration

## Slide 5: Agile development teams are typically comprised of three key groups, each performing critical roles…
Enable the team to build the thing fast (SM)
Build the right thing
(PO)
Build the thing right
(Dev Team)
Product owner (PO)
  Represents the business
  Ensures value delivery
  Acts as voice of the user
Scrum master (SM)
  Oversees the Scrum process and coaches the team
  Facilitates the removal of impediments to increase progress
  Enables cooperation across all roles and functions
Following true agile principles
  Technology + Innovation Lab able to transcend org. silos and fully integrated with business
  Team is dynamic, flexible, and includes business and technical roles
  12 weeks in total, with 2 week sprints. Daily stand-up/check-in to highlight milestones/roadblocks and steering committee every 2-4 weeks
  Delivers potentially shippable product at every sprint
  Staffed with cross-functional team members
  Is self-organizing and empowered
  Includes a Technology Head, who drives the technical direction of the project and coaches the team
Development Team

## Slide 6: Product teams may sit in a broader ecosystem of similar products that interact through communities
Product Teams
Multidisciplinary teams that sit together focused around product features.
Three key product team members:
Communities
Communities cut across product teams, consisting of same-role employees sharing best practices and expertise
Agile teams create nimbleness, increased productivity, and greater employee engagement
Communities foster sharing of best practices and knowledge
Key enablers are co-locating and integrating business and technical resources
Product owner (PO)
Scrum master (SM)
Development Team

## Slide 7: Product teams will also require detailed engagement from key external stakeholders
Stakeholder role
3 – 6 Users
1 – 3 SMEs
Business Product Sponsor and
IT Product Sponsor
Description
  Users to provide input on overall experience and feedback on application design and interaction model throughout Delivery
  Subject matter experts that can provide valuable input throughout Discovery and Delivery
  Senior leader committed to effort’s success, helping team clear roadblocks and obstacles. Provides strategic and problem solving input throughout the process

## Slide 8: These teams work in sprints to take ideas from business-backed backlog elements to deploy products
Sprint Planning
  Review product backlog
  Estimate sprint backlog
  Commit
Daily Stand up
  Progress since last stand up
  Plan for today
  Roadblocks/Impediments?
Sprint Review
  Demo features to all
  Retrospective on improving the next sprint
Sprint Retrospective
  Done after each sprint
  Aims to improve the process for next sprint
Product Backlog
Sprint Backlog
Dev team
Dev team
Time-boxed Test/Develop
(No changes)
Product Backlog
  User focused prioritized product features
Product Owner
Time-boxed “Sprint” Cycles
  Agile allows teams of people to develop complex products in environment of uncertainty and change
  Agile is a simple but powerful framework for teams and users to inspect and adapt as product is produced
  Agile provides a high degree of clarity and transparency to everyone involved: team, users, users, stakeholders
  Agile rapidly surfaces dysfunction and enables teams and organizations to continuously improve their effectiveness
I
IV
III
Dev team
Dev team
Backlog refinement
  Features for a Sprint
  Estimated by team
  Team commitment
Scrum Master
II
V
Working code ready for deployment

## Slide 9: Each element of the process is supported by a ceremony
Ceremony
Inputs
Activities
Outputs
  Sprint Planning
  Team capacity (SM)
  Planning velocity (SM)
  Prioritized Product Backlog (PO)
  Sprint goal (Team)
  Sprint backlog (Team)
  Review prioritized backlog (Team)
  Elaborate stories (PO)
  Create sprint goal (Team)
  Estimate tasks based on DoD / Development best practices (Team)
  Consider high-level design (Team)
  Sprint goal
  Sprint backlog
  Sprint plan (Team)
  Backlog grooming
  Up to date feedback from sprint review
  Feedback from users
  Discuss new stories for the backlog
  Review stories and acceptance criteria with the team
  Estimate stories
  Updated and prioritized product backlog (PO)
  Technical spikes (team)
  Business spikes (PO)
  Daily Stand-Up
  Updated deployment board (Team)
  List of impediments to resolve (SM)
  Answer the following questions:
    What I did yesterday
    What I will do today
    What impediments I have
  Deployment board (Team)
  Sprint Review
  Potentially shippable increment of software
  Metrics from the sprint
  Updated MVP delivery plan
  Demonstrate the stories developed in the sprint (Team)
  Discuss feedback (All)
  Create new stories (PO)
  Update on deployment progress
  Signed off stories (PO)
  Improvements (PO)
  New stories (PO)
  Sprint Retro-spective
  Actions for improvement (SM)
  Discuss sprint (Team)
  Present sprint metric (SM)
  Identify good and bad parts of the sprint (Team)
  Identify actions for improvement (Team)
  Sprint metrics (SM)
  PO = Product Owner SM = Scrum Master
I
II
III
IV
V

## Slide 10: Sprint Planning
SOURCE: McKinsey
I
Guidelines
  Held at the end of each Sprint
  Typically 2-3 hrs for a 2 week sprint
  Deployment wall or digital backlog is used to facilitate the discussion
Who are the attendees?
  Product Owner
  Scrum Master
  Full dev team
  SMEs
Product backlog
Sprint backlog
2 weeks
24 hours
Daily Huddle
Potentially shippable product increment
This side up
Product Owner
  Assesses progress made against the deployment goals and changes based on sprint feedback
  Presents sprint priorities to be considered in form of stories
  Elaborates detailed acceptance criteria for each story
The Team
  Creates the sprint goals
  Reviews prioritized backlog
  Assesses stories they can commit to base on DoD and development best practices
  Considers high-level design
The Scrum Process
The Sprint Planning meeting is used for the team to plan what can be accomplished during the next sprint

## Slide 11: Backlog refinement
Guidelines
  1 – 2 times during the sprint
  Can happen anytime during the sprint
  Product Owner prepares and runs the meeting
Who are the attendees?
  Product Owner
  Scrum Master
  IT Architect + team (not mandatory for all team members)
Product Owner
  Discusses feedback from sprint review
  Shares user feedback
  Updates and prioritizes user stories
  Reviews stories and acceptance criteria in collaboration with the team
The Team
  Identifies technical or business spikes
  Gains functional clarity from Product Owner on new/updated stories
  Discusses implementation options
  Estimates stories
  Influences priority based on technical dependencies
The Scrum Process
The backlog refinement meeting is used to refine the backlog: define stories, acceptance criteria, details and priority such that highest priority stories ready for work.
Product backlog
Sprint backlog
2 weeks
24 hours
Daily stand up
Potentially shippable product increment
This side up
Sprint planning
II

## Slide 12: Daily stand-up
Impediments identified during daily Scrum are added to the team impediments list
Three questions
  What did I do yesterday?
  What do I plan to do today?
  What impediments do I have?
  Kudos and Admin
Parameters
  Daily
  15-minutes
  Stand-up
  Not for problem solving
  Team members and stakeholders are invited. Only those committed share updates
  Helps avoid other unnecessary meetings
The Scrum Process
Goal of the daily huddle is for the team to understand its status each day in order to do a daily “inspect and adapt cycle”. The team reports to itself for 15 minutes regarding 3 questions
2 weeks
24 hours
Daily huddle
This side up
Team impediments
III

## Slide 13: Sprint Review
The Sprint Review is used to demonstrate what was accomplished during the Sprint. The team
  Presents stories committed to and completed
  Demonstrates new features
  Seeks feedback from leadership and stakeholders
  Assesses progress made against the deployment goals
  Reviews critical actions and KPIs
  Reviews updates or changes to backlog
Demonstrate the Product
Is THIS what you asked for?
Review the deployment Progress
Who are the attendees?
  Tribe Leadership
  Key stakeholders
  Members of dev team
  External teams (e.g., support)
  Invite the WORLD?
Guidelines
Typically 30 minutes of dry run / preparation time for the meeting
Demo software and share progress preferably with minimal slides
Held at the end of each Sprint
IV

## Slide 14: Sprint Retrospective
Retrospective creates an “inspect and adapt” cycle for how a team works together and alters their practices to improve productivity
Team gets together to answer 3 questions
  What is working well (should stay)?
  What is not working well (should change)?
  What do we need to do to get better (start)?
Outcome
  Team prioritizes 2-3 areas of focus and assigns ownership
  Team devises solution to most vexing problems
The Scrum Process
The Sprint Retrospective is a regular review of the team and its process. Focuses on "how" the team is building software and identifies how to get better for the next sprint
2 weeks
24 hours
Daily huddle
This side up
Inspect
Adapt
Act
Sprint Retrospective
Parameters
  End of each sprint
  Approximately 30 minutes to 1 hour
  Facilitated by a Scrum Master
  Attended by all team members
Product backlog
Sprint backlog
Potentially shippable product increment
Sprint Retrospective
V